## Simple Budget
Colorado Water Conservation Board
Watershed Restoration Program Grant
Budget and Schedule
Prepared Date: 3/12/2021
Name of Applicant: Mountain Studies Institute on behalf of Upper San Juan Watershed Enhancement Partnership
Name of Water Project: San Juan Integrated Water Management Plan, Phase III
Project Start Date:
Project End Date:
Task No. | Task Description | Task Start Date | Task End Date | CWRP Grant Funding Request | WSRF Statewide Funding Request | WSRF Basin Funding Request | Match Funding | Total
1 | Program Coordination & Stakeholder Engagement | 2021-06-01 | 2023-06-30 | 17375 | 7818.75 | 868.75 | 26893.42 | 52955.92
2 | Agricultural Infrastructure Analysis | 2021-06-01 | 2023-06-30 | 14875 | 6693.75 | 743.75 | 13187.5 | 35500
3 | Finalize Integrated Water Management Plan | 2021-06-01 | 2023-06-30 | 12500 | 5625 | 625 | 6250 | 25000
4 | Project/Grant Management | 2021-06-01 | 2023-06-30 | 4475 | 2013.75 | 224 | 2282 | 8994.75
5 | [7 empty] | 0
6 | [7 empty] | 0
Total |  |  |  | 49225 | 22151.25 | 2461.5 | 48612.92 | 122450.67
Page 1 of 1

## MSI Detailed Budget
|  |  | Project Management & Facilitation (MSI) |  |  | Community Liason (WW) |  |  | Technical Contractors (SJCD & Lotic) |  |  | Project Totals | In-Kind Hours
Project Tasks | Target Start Date | Target End Date | Unit | Rate/hr | Total | Unit | Rate/hr | Total | Unit | Rate/hr | Total |  | Unit | Rate/hr | Total | Total CWCB Funds | Cash Match | In-Kind Match | Source of Matching Funds | Combined Totals
Task 1: Project Management & Stakeholder Engagement | 2021-06-01 | 2023-06-30
Subtask 1.1: Project Oversight & Coordination |  |  | 90 | 65 | 5850 | - | - | - | - | - | - |  | 160 | 50 | 8000 |  | 500 | 8000 | Mountain Studies Institute (Cash), Trout Unlimited (In-kind)
Subtask 1.2: Project Coordination, Facilitation, Education Resources |  |  | 350 | 45 | 15750 | - | - | - | - | - | - |  | 9 | 56.04 | 6052.32 |  | 1000 | 6052.32 | The Nature Conservancy (Cash), Steering Committee (In-Kind)
Subtask 1.3: Community Outreach, Project Support, Long-term Plan |  |  | - | - | - | 270 | 45 | 12150 | - | - | - |  | 4 | 51.92 | 4153.6 |  | 2000 | 4153.6 | Trout Unlimited (Cash), Public Meetings (In-Kind)
Outreach printing/publishing costs |  |  | 50 | 20 | 1000 | - | - | - | - | - | -
Task 1 Total |  |  | 490 | varies | 22600 | 270 | 45 | 12150 | - | - | - | 34750 |  |  | 18205.92 | 26062.5 | 3500 | 18205.92 |  | 47768.42
Task 2: Agricultural Infrastructure Analysis | 2021-06-01 | 2023-06-30
Subtask 2.1: Data Review, Inventory, Prioritize Projects |  |  | - | - | - | - | - | - | 650 | 35 | 22750 |  | 50 | 35 | 1750 |  | 8100 | 1750 | Southwestern Water Conservation District (Cash), SJCD Staff (In-Kind)
Subtask 2.2: Data Access, Inventory Oversight |  |  | - | - | - | - | - | - | 200 | 35 | 7000 |  | 100 | 40 | 4000 |  |  | 4000 | Natural Resource Conservation Services Staff (In-Kind)
Task 2 Total |  |  | - | - | - | - | - | - | 850 | 35 | 29750 | 29750 |  |  | 5750 | 22312.5 | 8100 | 5750 |  | 36162.5
Task 3: Finalize Integrated Water Management Plan | 2021-06-01 | 2023-06-30
Subtask 3.1: Develop Management Goals & Objectives |  |  | - | - | - | - | - | - | 32 | 125 | 4000 |  | - | - | - |  | 2000 |  | San Juan Water Conservancy District (Cash)
Subtask 3.2: Identify Candidate Actions, Projects & Processes |  |  | - | - | - | - | - | - | 32 | 125 | 4000 |  | - | - | - |  | 3600 |  | Archuleta County Board of County Commissioners (Cash)
Subtask 3.3: Evaluate & Prioritize Alternatives |  |  | - | - | - | - | - | - | 68 | 125 | 8500 |  | - | - | - |  | 3600 |  | Pagosa Tourism Board (Cash)
Subtask 3.4: Plan for Implementation |  |  | - | - | - | - | - | - | 40 | 125 | 5000 |  | - | - | - |  | 3857 |  | Town of Pagosa Springs (Cash)
Subtask 3.5: Develop Final Planning Document |  |  | - | - | - | - | - | - | 28 | 125 | 3500 |  | - | - | -
Task 3 Total |  |  | - | - | - | - | - | - | 200 | 125 | 25000 | 25000 | - | - | - | 18750 | 13057 | 0 |  | 31807
Project/Grant Management |  |  | subtotal | 10% | 8950 | [6 empty] | 8950 |  |  |  | 6712.75 |  |  |  | 6712.75
TOTALS |  |  |  |  | 31550 |  |  | 12150 |  |  | 54750 | 98450 |  |  | 23955.92 | 73837.75 | 24657 | 23955.92 |  | 122450.67
*In-kind hour rates for Steering Committee Meetings used professional/expert volunteer rate of $28.02/hr for 12 people for two hours.
**In-kind hour rates for Public Meetings used Colorado volunteer rate of $25.96/hr for 20 people for two hours. These numbers are conservative, but hope to have more than 20 people participate in each public meeting.

## Detailed-Study
Colorado Water Conservation Board
Watershed Restoration Program Grant - Detailed Budget Estimate
Fair and Reasonable Estimate
Prepared Date:
Name of Applicant:
Name of Water Project:
EXAMPLE A: Study or Project Coordination
Task 1 - [TASK NAME]
Sub-task | Item | Hourly Rate | # Hours | Sub-total |  | Item Cost | Item Quantity | Sub-total | Total | CWRP Funds | WSRF Funds | Matching Funds
Focus Groups
| Participant Stipend |  |  | 0 |  | 50 | 20 | 1000 | 1000 | 250 |  | 750
| Catering |  |  | 0 |  | 15 | 20 | 300 | 300 | 75 |  | 225
| Feedback Survey |  |  | 0 |  | 0.5 | 20 | 10 | 10 | 2.5 |  | 7.5
| Staff Time | 40 | 10 | 400 |  |  |  |  | 400 | 100 |  | 300
Develop Exhibit
| Exhibit Designer | 50 | 100 | 5000 |  |  |  | 0 | 5000
| Staff Time Project Manager | 50 | 30 | 1500 |  |  |  | 0 | 1500
| Staff Time Administrative | 35 | 20 | 700 |  |  |  | 0 | 700
| Film Production (filming, editing, production) |  |  | 0 |  | 5000 | 1 | 5000 | 5000
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
TOTAL | [8 empty] | 13910
Other Direct Costs (see below) | [8 empty] | 2469
OVERALL TOTAL | [8 empty] | 16379
Other Direct Costs
Item: | Copies & Printing (Black & White) | Copies & Printing (Color) | Materials and Final Report Production | Lodging and Meals | Travel Expenses (Airfare and Car Rental) | Mileage | Total
Units: | No. | No. | Lump Sum | Per Diem | Lump Sum | Miles
Unit Cost: | 0.1 | 0.5 |  | 100 |  | 0.535
Project Initiation | 150 | 100 |  | 2 |  | 400 | 479
Report, Conclusions and Recommendations | 150 | 150 | 1900 | 0 |  | 0 | 1990
Total Units: | 300 | 250 | 1900 | 2 | 0 | 400
Total Cost: | 30 | 125 | 1900 | 200 | 0 | 214 | 2469