## Simple Budget
Upper San Juan Basin Integrated Water Management Plan, Phase II: Budget and Timeline
Task | Description | Target Start Date | Target Completion Date* | CWCB Funds WRP | CWCB Funds WSRF | Other Funding Cash | Other Funding In-Kind | Total
1 | Coordination & Stakeholder Engagement | 2020-05-01 | 2022-05-31 | 21799.7 | 10899.85 | 10899.85 | 18026.8 | 61626.2
| Grant Administration | 2020-05-01 | 2022-05-31 | 7810.32 | 3905.16 | 3913 |  | 15628.48
2 | Agricultural Water Needs Analysis | 2020-05-01 | 2022-05-31 | 19705 | 9852.5 | 9852.5 | 10030 | 49440
3 | Technical Analysis + Modeling | 2020-05-01 | 2022-05-31 | 36598.5 | 18299.25 | 18299.25 |  | 73197
| TOTALS |  |  | 85913.52 | 42956.76 | 42964.6 | 28056.8 | 199891.68
*extra year built in to end date to accommodate any potential delays

## Detailed Budget
|  |  | Project Management & Facilitation (MSI) |  |  | Community Liason (WW) |  |  | Technical Contractors (SJCD & Lotic) |  |  | Grant Administration (MSI) |  |  | In-Kind Hours
Task | Target Start Date | Target End Date | Unit | Rate | Total | Unit | Rate | Total | Unit | Rate | Total | Unit | Rate | Total | Unit | Rate | Total | Combined CWCB Funds | Cash Match | In-Kind Match | Source of Matching Funds | Total
Task 1: Coordination & Stakeholder Engagement | 2020-05-01 | 2022-05-31 | [12 empty] | 160 | 50 | 8000 | 32699.55
Subtask 1.1: Meeting Facilitation, Project Management |  |  | 120 | 65 | 7800 | - | - | - | - | - | - | - | - | - | 15 | 56.04 | 5043.6 |  | 1957 | 8000 | Mountain Studies Institute (cash), Trout Unlimited (in-kind)
Subtask 1.2: Coordination, Stakeholder Engagement |  |  | 416 | 45 | 18720 | - | - | - | - | - | - | - | - | - | 30 | 51.92 | 3115.2 |  | 1000 | 5043.6 | The Nature Conservancy (cash), WEP Steering Commitee (in-kind)
Subtask 1.3: Community Outreach, Project Support |  |  | - | - | - | 334 | 45 | 15030 | - | - | - | - | - | - | 2 | 350 | 700 |  | 2000 | 3115.2 | Trout Unlimited (cash), public volunteer (in-kind)
Subtask 1.4: Grant Administration |  |  | - | - | - | - | - | - | - | - | - | subtotal | 10% | 15628.48 | - | - | - | 11715 | 2500 | 348 | Town of Pagosa Springs (cash), WEP Steering Committee (in-kind)
Posters |  |  | 50 | 20 | 1000 | - | - | - | - | - | - | - | - | - | 6 | 120 | 720 |  | 2000 | 700 | San Juan Water Conservancy District (cash), CSU-Extension Office (in-kind)
Meeting Supplies |  |  | 750 | 0.1 | 75 | - | - | - | - | - | - | - | - | - | 2 | 50 | 100 |  | 2500 | 720 | Pagosa Tourism Board (cash), Town of Pagosa Springs (in-kind)
Travel |  |  | 14 | 0.58 | 974.4 | - | - | - | - | - | - | - | - | - | 100 | 0.58 | 348 |  | 2856 | 100 | Banded Peak Ranch (partial, cash), Archuleta County (partial cash), Pagosa Brewing (in-kind)
Task 1 Total |  |  | 1350 | varies | 28569.4 | 334 | 45 | 15030 | - | - | - | - | - | 15628.48 | 315 | varies | 18026.8 | 44414.55 | 14813 | 18026.8 |  | 77254.35
Task 2: Agricultural Water Needs Analysis | 2020-05-01 | 2022-05-31
Subtask 2.1: Data Review, Inventory, Prioritize Projects |  |  | - | - | - | - | - | - | 840 | 35 | 29400 | - | - | - | 58 | 35 | 2030 |  | 9853 | 2030 | Banded Peak Ranch (partial, cash), San Juan Conservation District (in-kind)
Subtask 2.2: Data Access, Inventory Oversight |  |  | - | - | - | - | - | - | 286 | 35 | 10010 | - | - | - | 200 | 40 | 8000 |  |  | 8000 | National Resources Conservation Service/San Juan Conservation District (in-kind)
Task 2 Total |  |  | - | - | - | - | - | - | 1126 | 35 | 39410 | - | - | - | 258 | varies | 10030 | 29557.5 | 9853 | 10030 |  | 49440.5
Task 3: Technical Analysis & Modeling | 2020-05-01 | 2022-05-31
Subtask 3.1: Consultant Team & Stakeholder Meetings |  |  | - | - | - | - | - | - | 17.8571 | 140 | 2500 | - | - | - | - | - | -
Subtask 3.2: Final Presentation |  |  | - | - | - | - | - | - | 2.9786 | 140 | 417 | - | - | - | - | - | -
Subtask 3.3: Project Coordination |  |  | - | - | - | - | - | - | 22.8214 | 140 | 3195 | - | - | - | - | - | -
Subtask 3.4: Travel |  |  | - | - | - | - | - | - | 19.8429 | 140 | 2778 | - | - | - | - | - | -
Subtask 3.5: Kickoff Meeting |  |  | - | - | - | - | - | - | 8.3143 | 140 | 1164 | - | - | - | - | - | -
Subtask 3.6: Stakeholder Engagement Plan Assistance |  |  | - | - | - | - | - | - | 4.6143 | 140 | 646 | - | - | - | - | - | -
Subtask 3.7: Review Existing Data |  |  | - | - | - | - | - | - | 15.2357 | 140 | 2133 | - | - | - | - | - | -
Subtask 3.8: Characterize & Model Hydrological Regimes |  |  | - | - | - | - | - | - | 34.0643 | 140 | 4769 | - | - | - | - | - | - |  | 17158 |  | Southwestern Water Conservation District (cash)
Subtask 3.9: Characterize Ecological Integrity |  |  | - | - | - | - | - | - | 121.0143 | 140 | 16942 | - | - | - | - | - | -
Subtask 3.10: Explore Water/Forest Health Nexus |  |  | - | - | - | - | - | - | 98.6071 | 140 | 13805 | - | - | - | - | - | -
Subtask 3.11: Characterize Recreational Uses |  |  | - | - | - | - | - | - | 123.7 | 140 | 17318 | - | - | - | - | - | -
Subtask 3.12: Identify Priority Management Issues |  |  | - | - | - | - | - | - | 53.7857 | 140 | 7530 | - | - | - | - | - | - |  | 1141 |  | Archuleta County Board of County Commissioners (partial, cash)
Task 3 Total |  |  | - | - | - | - | - | - | 522.8357 | 140 | 73197 | - | - | - | - | - | - | 54897.75 | 18299 | - |  | 73196.75
TOTAL |  |  |  |  | 28569.4 |  |  | 15030 |  |  | 112607 |  |  | 15628.48 |  |  | 28056.8 | 128869.8 | 42965 | 28056.8 |  | 199891.6

## Matching Funds
Project Total | 171827.04 | Percentage of Project Total
CWCB WRP | 85913.52 | 50%
SWBRT (CWCB) WSRF | 42956.76 | 25%
Total CWCB Fund Request | 128870.28 | 75%
Cash Match | 41647 | 24.24%
In-kind Match | 28056.8 | 16.33%
Cash + In-kind Total | 69703.8 | 40.57%
In-kind Match | Amount
Trout Unlimited Advising Services (160 hrs @ $50/hr) | 8000
Steering Committee/Consultant Meetings (2 hrs x 28.02 CO volunteer rate = $56.04 x 15 pax = $840.60 x 6 meetings) | 5043.6
Mileage for 6 Steering Committee Meetings ($0.58/mile) ranges $50-$150 | 348
Public meetings (2 hrs x 25.96 volunteer rate = $51.92 x 30 pax = $1,557.60 x 2 meetings) | 3115.2
San Juan Conservation District Staff Time (57 hrs @ $35/hr) | 2030
Natural Resources Conservation Service Staff Time (200 hrs @ $40/hr) | 8000
Meeting Refreshments (Pagosa Brewing beverages $50 for 2 public meetings) | 100
CSU-Extension Office Facility Rental (2 public meetings at $350/day) | 700
Town Hall Facility Rental (6 meetings at $60/hr x 2 hrs) | 720
In-kind Total | 28056.8
Cash Match | Amount | Status
Mountain Studies Institute Staff Time | 1957 | Committed
The Nature Conservancy | 1000 | Committed
Trout Unlimited | 2000 | Committed
Banded Peak Ranch | 11000 | Committed
Southwestern Water Conservation District* | 17158 | Committed
San Juan Water Conservancy District | 2000 | Committed
Town of Pagosa Springs Tourism Board | 2500 | Committed
Town of Pagosa Springs* | 1182 | Committed
Archuleta County Board of County Commissioners | 2850 | Committed
Cash Match Total | 41647
* Reduced amount awarded than orginally requested

## Schedule
SCHEDULE
The first month will be spent gathering available assessment resources (i.e. data, reports, models, community surveys, etc.). Field work and lab analysis will be conducted for 7 months to develop models, maps, and identify priority areas. Meetings (in person or remote) between the consultants and project management team (MSI, TU, WW) will occur monthly for the duration of the project scope. The Steering Committee established in Phase I will be actively engaged in the process, with a total of 6 meetings with the committee, consultants, and project management team during Phase II. Public stakeholder meetings will be convened 2 times to allow community feedback into initial findings and developing subsequent planning objectives and project options (expressed in the schedule below).
Table 1.6: Schedule, Phase II
Tasks | Month (After Contract Initiation) | [11 empty] | Total # of Meetings
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Data Review + Conduct Analysis | X | X | X | X | X | X | X | X
Assessment Development | [8 empty] | X | X | X | X
Project Management Team/Consultants Meeting | X | X | X | X | X | X | X | X | X | X | X | X | 12
(6 in person, 6 remote)
Consultant/Steering Committee Meeting | X |  | X |  | X |  | X |  | X |  | X |  | 6
Public Meeting | [5 empty] | X | [5 empty] | X | 2